Rehearsal Number:	14		Time Started:	2:00
Date:	9/16/21		Time Ended:	4:00

Materials Covered:	Run through from the first task to the end of page 71 with puff cast
Time:	Who:	What:
2:30	Puff cast	First task-pg. 71 review

General Notes:	MEMORIZE YOUR LINES / WRITE DOWN YOUR BLOCKING AND PROPS YOU TAKE ON/OFF / Mark in scripts all of the times the bench goes on and off
SM Notes:	PLEASE MESSAGE YOUR STAGE MANAGER DIRECTLY IF YOU ARE NOT GOING TO BE AT REHEARSAL!!
Scenic Notes:	No notes
Lighting Notes:	No notes
Costume Notes:	Cedric patches need to be made in tech. / All cast members need a Halloween costume. / J. Finch needs a red shirt for Neville scene (pg. 33) / Look up hufflepuff outfits on pinterest and bring in items / Malfoy wig needs to be purchased or made / Accessory bags need to be set up / NO OPEN-TOED SHOES WHEN REHEARSING
Props Notes:	Most props have come in or have been ordered. / Prop tables need to be set up / “No being too sad” banner needs to be made / Large book for year five needs to be found/made
Sound Notes:	Soundboard is working again / We will try and run sound at the next time we’re in the auditorium
Auditorium Notes:	Note in your scripts which side of the stage you leave in for each scene / Prop tables need to be set up

Next Rehearsal:	9/20/2021
Materials to be covered:	Start on page 71 and continue blocking